## Projects
businessKey | name | status | clientName | currency | dataDate | plannedStart | plannedFinish | actualStart | actualFinish | budgetAtCompletion
P-1000 | Nile Tower — Main Construction | Active | Sigma Holdings | USD | 2026-05-15 | 2026-01-05 | 2026-12-18 | 2026-01-07 |  | 4200000

## Activities
businessKey | projectKey | wbsCode | name | activityType | status | plannedStart | plannedFinish | actualStart | actualFinish | plannedDurationDays | remainingDurationDays | plannedPctComplete | actualPctComplete | budgetedCost | actualCost
A1000 | P-1000 | 1.1 | Site Mobilisation | Task Dependent | Completed | 2026-01-05 | 2026-01-16 | 2026-01-07 | 2026-01-19 | 10 | 0 | 1 | 1 | 80000 | 86500
A1010 | P-1000 | 1.2 | Bulk Excavation | Task Dependent | Completed | 2026-01-19 | 2026-02-13 | 2026-01-21 | 2026-02-20 | 20 | 0 | 1 | 1 | 240000 | 268000
A1020 | P-1000 | 1.3 | Piling & Foundations | Task Dependent | In Progress | 2026-02-16 | 2026-04-10 | 2026-02-23 |  | 40 | 8 | 1 | 0.8 | 620000 | 540000
A1030 | P-1000 | 2.1 | Basement RC Structure | Task Dependent | In Progress | 2026-04-13 | 2026-06-19 | 2026-04-27 |  | 50 | 38 | 0.45 | 0.22 | 910000 | 210000
A1040 | P-1000 | 2.2 | Superstructure — Cores | Task Dependent | Not Started | 2026-06-22 | 2026-09-04 |  |  | 55 | 55 | 0 | 0 | 1180000 | 0
A1050 | P-1000 | 3.1 | MEP First Fix | Task Dependent | Not Started | 2026-08-10 | 2026-10-30 |  |  | 60 | 60 | 0 | 0 | 540000 | 0
A1060 | P-1000 | 3.2 | Facade Installation | Task Dependent | Not Started | 2026-09-07 | 2026-11-27 |  |  | 60 | 60 | 0 | 0 | 470000 | 0
A1070 | P-1000 | 4.1 | Commissioning & Handover | Task Dependent | Not Started | 2026-11-30 | 2026-12-18 |  |  | 15 | 15 | 0 | 0 | 160000 | 0

## Resources
businessKey | projectKey | name | resourceType | unitOfMeasure | maxUnitsPerDay | standardRate
R-CIVIL | P-1000 | Civil Crew A | labor | hours | 80 | 24
R-MEP | P-1000 | MEP Crew | labor | hours | 48 | 30
R-EXC | P-1000 | Excavator 30T | equipment | hours | 10 | 120
R-CONC | P-1000 | Concrete C40 | material | m3 |  | 95

## Reports
businessKey | projectKey | reportType | reportDate | periodStart | periodEnd | submittedBy | reportedPctComplete | narrative
RPT-W17 | P-1000 | weekly | 2026-05-01 | 2026-04-25 | 2026-05-01 | Site Engineer | 0.38 | Foundations nearing completion; basement RC slipped due to late rebar delivery.
RPT-W18 | P-1000 | weekly | 2026-05-08 | 2026-05-02 | 2026-05-08 | Site Engineer | 0.41 | Basement RC progressing slowly; piling at 80%. Concrete pour rate below plan.
RPT-W19 | P-1000 | weekly | 2026-05-15 | 2026-05-09 | 2026-05-15 | Project Manager | 0.44 | Schedule pressure on basement RC; recovery plan requested for cores start.

## Assignments
businessKey | activityKey | resourceKey | plannedUnits | actualUnits | plannedCost | actualCost
TR-1 | A1010 | R-EXC | 160 | 188 | 19200 | 22560
TR-2 | A1010 | R-CIVIL | 1200 | 1320 | 28800 | 31680
TR-3 | A1020 | R-CONC | 3200 | 2600 | 304000 | 247000
TR-4 | A1020 | R-CIVIL | 2400 | 2100 | 57600 | 50400
TR-5 | A1030 | R-CONC | 4100 | 900 | 389500 | 85500
TR-6 | A1030 | R-CIVIL | 3000 | 700 | 72000 | 16800