## README
Sigma PMO — Official Data Template
How to use:
1. Fill the sheets below. Each sheet maps to one entity. The header row names are the exact field keys the platform expects.
2. Keys link the data together: activity.projectKey = project.businessKey; assignment.activityKey = activity.businessKey;
assignment.resourceKey = resource.businessKey; resource/report.projectKey = project.businessKey.
3. Dates use ISO format YYYY-MM-DD. Numbers are plain (no thousands separators).
4. Upload this .xlsx on the Input page. Empty files (zero records) are rejected with a clear message.
Required minimum: at least the Projects sheet + the Activities sheet, linked by projectKey.
The sample rows already in each sheet ingest successfully — replace them with your data.
Data chain after ingestion: file -> activities/records -> alerts -> decisions -> evidence -> approvals -> executive/governance dashboards.

## Projects
businessKey | name | status | clientName | currency | dataDate | plannedStart | plannedFinish | actualStart | actualFinish | budgetAtCompletion
P-1000 | Hospital Tower — Phase 1 | active | Ministry of Health | SAR | 2026-06-01 | 2026-01-01 | 2027-06-30 |  |  | 48000000

## Activities
businessKey | projectKey | wbsCode | name | activityType | status | plannedStart | plannedFinish | actualStart | actualFinish | plannedDurationDays | remainingDurationDays | plannedPctComplete | actualPctComplete | budgetedCost | actualCost
A-1001 | P-1000 | 1.1 | Site mobilisation | Task | completed | 2026-01-01 | 2026-01-20 | 2026-01-01 | 2026-01-22 | 20 |  | 100 | 100 | 500000 | 540000
A-1002 | P-1000 | 1.2 | Excavation | Task | in_progress | 2026-01-21 | 2026-03-15 |  |  | 54 |  | 60 | 45 | 2200000 | 1100000

## Resources
businessKey | projectKey | name | resourceType | unitOfMeasure | maxUnitsPerDay | standardRate
R-100 | P-1000 | Excavator | Equipment | hours | 8 | 350

## Assignments
businessKey | activityKey | resourceKey | plannedUnits | actualUnits | plannedCost | actualCost
AS-1 | A-1002 | R-100 | 432 | 200 | 151200 | 70000

## Reports
businessKey | projectKey | reportType | reportDate | periodStart | periodEnd | submittedBy | reportedPctComplete | narrative | metrics
RP-1 | P-1000 | weekly | 2026-06-01 | 2026-05-26 | 2026-06-01 | Site Engineer | 38 | Excavation behind plan by ~10 days due to rock.